## Gantt_ds_connector
ID | Task | Sub Task | Resource Name | Column2 | Primary ConnectorType | Primary ConnectTo | ActualStart | ActualEnd | PlannedStart | PlannedEnd | Progress | Turn Around E | Rank | Milestone
1 | REQUIREMENTS | Requirements Gathering | Earl King | In progress | FinishStart | Kimberly | 2/28/2017 | 2017-05-03 | 2/23/2017 | 2017-09-03 | 66 | 1 | 1
2 | REQUIREMENTS | Project Plan | Jack | In progress |  |  | 2017-07-03 | 2017-07-15 | 2017-05-03 | 3/21/2017 | 44 | 3 | 2
3 | REQUIREMENTS | Walkthroughs | John & Earl King | Completed | StartFinish | Randy | 2/27/2017 | 2/27/2017 | 2/27/2017 | 2/27/2017 | 100 | 1 | 3
4 | DESIGN | Busines Case Preparation | Randy | In progress |  |  | 2/27/2017 | 3/15/2017 | 2/24/2017 | 3/19/2017 | 32 | 3 | 4 | 2017-03-10
5 | DESIGN | Systems architecture | Randy | In progress |  |  | 2017-05-03 | 2017-06-19 | 2017-05-03 | 2017-06-24 | 99 | 2 | 5
6 | DESIGN | UI/UX | Mai | Not Started |  |  | 2/23/2017 | 2017-03-20 | 2/18/2017 | 3/16/2017 | 42 | 3 | 6
7 | DESIGN | Design Walkthrough | Mai | Not Started | FinishFinish | Randy | 2/27/2017 | 3/15/2017 | 2/25/2017 | 3/19/2017 | 0 | 3 | 10 | 2017-03-10
8 | DESIGN | Review | Earl King & Mai | Not Started |  |  | 2017-03-16 | 2017-03-16 | 2017-03-19 | 2017-03-19 | 0 | 3 | 10
9 | DEVELOPMENT | Internal Audit | Larry | Not Started | StartStart | Jack | 2017-05-03 | 2017-05-31 | 2017-05-03 | 2017-06-06 | 0 | 3 | 7
10 | DEVELOPMENT | Actual Product Development | Laura | Not Started |  |  | 3/15/2017 | 3/18/2017 | 3/13/2017 | 3/24/2017 | 0 | 1 | 8
11 | DEVELOPMENT | Peer Review | Marin | Not Started |  |  | 2017-06-20 | 2017-08-01 | 2017-06-20 | 2017-07-31 | 0 | 3 | 9